# PROJECT CHARTER

# Da'atSNA Community Data Platform

Version 1.0 | 2026-01-01 – 2026-12-31

# 1. EXECUTIVE SUMMARY

Da'atSNA Community Data Platform is sponsored by Dr. James Okello, Project Sponsor — Min. of Health and managed by Sarah Nakato. Enable every community health worker in Uganda to access trusted, interoperable patient data through a secure national platform.

# 2. PROJECT OVERVIEW

| Field | Value |
| --- | --- |
| Project Name | Da'atSNA Community Data Platform |
| Project Sponsor | Dr. James Okello, Project Sponsor — Min. of Health |
| Project Manager | Sarah Nakato |
| Department/Division | Digital Health Innovations |
| Start Date | 2026-01-01 |
| End Date | 2026-12-31 |

# 3. VISION & OBJECTIVES

## 3.1 Vision Statement

Enable every community health worker in Uganda to access trusted, interoperable patient data through a secure national platform.

## 3.2 Mission Statement

Design, build, and deploy the Da'atSNA Community Data Platform connecting clinics, NHIS, and ministry systems within 12 months.

## 3.3 SMART Objectives

| ID | Objective | Measurable Criteria |
| --- | --- | --- |
| OBJ-01 | Deliver FHIR-compliant data exchange between 50 pilot clinics | 50 clinics live by Q4; 99% uptime SLA |
| OBJ-02 | Reduce patient record retrieval time for CHWs | Median query time under 2 seconds |
| OBJ-03 | Train 200 community health workers on the platform | 200 certified users; 80% adoption in pilot districts |

# 4. SCOPE

## 4.1 In-Scope

FHIR API gateway and patient demographics module

Clinic onboarding portal and CHW mobile interface

Integration with NHIS billing endpoints

Training program and operational runbooks

## 4.2 Out-of-Scope

Payroll and HR systems

Legacy paper record digitization backlog

National e-prescription rollout (Phase 2)

## 4.3 Boundaries

Platform terminates at approved ministry firewall endpoints; clinics connect via VPN or approved cloud links.

## 4.4 Scope Diagram

Figure 1: Scope Boundaries

# 5. STAKEHOLDERS

## 5.1 Stakeholder Register

| ID | Name | Role | Organization | Power | Interest |
| --- | --- | --- | --- | --- | --- |
| SH-01 | Dr. James Okello | Project Sponsor | Min. of Health | High | High |
| SH-02 | Dr. Sarah Nambi | Policy Maker | Min. of Health | High | Low |
| SH-03 | NHIS Leadership | Insurance Partner | NHIS | High | High |
| SH-04 | District Health Officers | Regional Coordinators | Regional Health Offices | Low | High |
| SH-05 | Community Health Workers | End Users | Pilot Clinics | Low | High |

## 5.2 Stakeholder Matrix

Figure 2: Power-Interest Matrix

# 6. SYSTEM CONTEXT

System context diagram (when provided).

# 7. PROJECT ORGANIZATION

## 7.1 Team Structure

| ID | Name | Role | Reports To |
| --- | --- | --- | --- |
| SPONSOR | Dr. James Okello | Project Sponsor | — |
| PM | Sarah Nakato | Project Manager | SPONSOR |
| TL-TECH | David Mukasa | Technical Lead | PM |
| TL-QA | Grace Achieng | QA Lead | PM |
| BA-01 | Peter Okello | Business Analyst | PM |

## 7.2 Org Chart

Figure 3: Project Organization

# 8. CONSTRAINTS & ASSUMPTIONS

## 8.1 Constraints

Must comply with Uganda Data Protection and Health Information regulations

Total budget capped at USD 59,400 for Phase 1

All production releases require sponsor sign-off

## 8.2 Assumptions

Existing NHIS APIs remain stable through project duration

Pilot clinics provide dedicated IT liaisons

Cloud infrastructure procured within first 60 days

Ministry security review completes before go-live

# 9. RISKS

## 9.1 Risk Register

| ID | Risk | Likelihood | Impact | Mitigation |
| --- | --- | --- | --- | --- |
| RSK-01 | NHIS API changes break billing integration | 3 | 4 | Maintain adapter layer; monthly API compatibility review with NHIS |
| RSK-02 | Clinic connectivity delays pilot rollout | 4 | 3 | Pre-site surveys; backup mobile hotspot kits for 10 clinics |
| RSK-03 | Security audit findings delay go-live | 2 | 5 | Early penetration test in Q2; remediate findings before UAT |

## 9.2 Problem Tree Analysis

Figure 4: Problem Tree

## 9.3 Risk Matrix

Figure 5: Risk Matrix

# 10. MILESTONES

## 10.1 Milestone Schedule

| ID | Milestone | Date | Deliverable |
| --- | --- | --- | --- |
| M1 | Project Kickoff | 2026-01-01 | Charter approved; team mobilized |
| M2 | Architecture Sign-off | 2026-03-15 | Solution architecture and security baseline approved |
| M3 | Pilot Go-Live | 2026-09-01 | 10 clinics live on platform |
| M4 | Phase 1 Complete | 2026-12-15 | 50 clinics connected; training complete |

## 10.2 Timeline

Figure 6: Milestone Timeline

# 11. BUDGET

| Category | Amount (USD) |
| --- | --- |
| Personnel | 31,000 |
| Hardware | 18,500 |
| Software | 1,500 |
| Training | 3,000 |
| Contingency | 5,400 |
| TOTAL | 59,400 |

# 12. SUCCESS CRITERIA

50 clinics connected with verified data exchange

Median record retrieval under 2 seconds

200 CHWs trained and actively using the platform

Zero critical security findings at go-live audit

# 13. APPROVALS

| Role | Name | Signature | Date |
| --- | --- | --- | --- |
| Project Sponsor | Dr. James Okello |  | 2026-01-05 |
| Project Manager | Sarah Nakato |  | 2026-01-05 |