# PROJECT CHARTER

# National Integrated Healthcare Ecosystem (NIHE)

Version 1.1 | 2026-07-01 – 2028-09-30

# 1. EXECUTIVE SUMMARY

National Integrated Healthcare Ecosystem (NIHE) is sponsored by Ministry of Health, Uganda and managed by Project Manager, Digital Health Division. To create a secure, interoperable, GIS-enabled healthcare ecosystem that connects patients, healthcare providers, regulators, and researchers through a unified digital platform across Uganda.

# 2. PROJECT OVERVIEW

| Field | Value |
| --- | --- |
| Project Name | National Integrated Healthcare Ecosystem (NIHE) |
| Project Sponsor | Ministry of Health, Uganda |
| Project Manager | Project Manager, Digital Health Division |
| Department/Division | Ministry of Health - Digital Health Division |
| Start Date | 2026-07-01 |
| End Date | 2028-09-30 |

# 3. VISION & OBJECTIVES

## 3.1 Vision Statement

To create a secure, interoperable, GIS-enabled healthcare ecosystem that connects patients, healthcare providers, regulators, and researchers through a unified digital platform across Uganda.

## 3.2 Mission Statement

To digitize and integrate healthcare services, improve accessibility, enable emergency response coordination, support telemedicine, enhance regulatory oversight, protect patient data, and facilitate national health analytics through a single, scalable, and sustainable platform.

## 3.3 SMART Objectives

| ID | Objective | Measurable Criteria |
| --- | --- | --- |
| OBJ-01 | Digitize healthcare records and enable seamless sharing across facilities | Patient record retrieval time ≤ 2 seconds; 100% of registered facilities using EHR |
| OBJ-02 | Improve healthcare accessibility through GIS-enabled facility discovery and navigation | 100% of districts covered; facility location accuracy ≤ 10m |
| OBJ-03 | Enable emergency response coordination with real-time dispatch and tracking | Emergency dispatch time ≤ 2 minutes; patient location accuracy ≤ 50m |
| OBJ-04 | Support telemedicine services for remote consultation and care | Video consultation connection success rate ≥ 95%; patient satisfaction ≥ 4/5 |
| OBJ-05 | Improve regulatory oversight through compliance monitoring and pharmacovigilance | Regulatory compliance rate 100%; ADR report acknowledgment ≤ 4 hours |
| OBJ-06 | Enable national health analytics and public health surveillance | Surveillance data freshness ≤ 5 minutes; outbreak detection ≤ 48 hours |
| OBJ-07 | Facilitate interoperability with existing healthcare systems | HL7/FHIR standards compliance ≥ 95%; integration success rate ≥ 95% |
| OBJ-08 | Protect patient data privacy and platform security through robust cybersecurity controls and compliance | Zero critical (Severity 1) security incidents per year; 100% of facilities completing annual security awareness training; full compliance verified in annual Data Protection Act audits |
| OBJ-09 | Build sustainable digital health capacity among healthcare workers and facility administrators | ≥ 90% of onboarded healthcare personnel certified on platform use within 60 days of facility go-live; digital health literacy training delivered in all 146 districts |

# 4. SCOPE

## 4.1 In-Scope

Patient-facing services: account management, EHR access, appointment booking, telemedicine, AI health assistant, facility discovery and navigation, emergency assistance, online pharmacy, payments, health monitoring, medication reminders, pharmacovigilance reporting, reviews and notifications

Health facility services: registration and verification, staff and patient management, EMR, telemedicine, pharmacy and laboratory operations, order and delivery management, emergency services, location and mapping, financial management, reviews, pharmacovigilance, reporting, and notifications

Healthcare personnel services: professional profile management, availability and scheduling, patient search and access, clinical consultation management, telemedicine, prescription management, laboratory and diagnostic requests, referral management, emergency response, pharmacist and laboratory functions, care coordination, pharmacovigilance, health monitoring, reviews, reporting, and notifications

System administration: user, facility, and personnel lifecycle management; content and catalog governance; transaction oversight; security and audit administration; system configuration; monitoring; backup and recovery

Regulatory oversight: facility and personnel oversight; prescription and medicine oversight; pharmacovigilance management; public health surveillance; inspection management; complaint investigation; national health analytics

Audit capabilities: audit trail management; compliance auditing; financial auditing; security auditing

Developer ecosystem: REST and GraphQL APIs; webhooks; SDKs; plugin framework; healthcare interoperability standards (HL7, FHIR, ICD, SNOMED CT, LOINC)

GIS capabilities: facility geocoding; map tile services; routing and navigation; geospatial analytics; emergency location services

Security, privacy, and compliance services: end-to-end encryption, encryption key management, consent management, role-based access control, access auditing, and data subject rights handling under Uganda's Data Protection and Privacy Act

Capacity building and support: healthcare-worker digital literacy training, facility administrator onboarding, multi-channel help desk and support services, district-level adoption dashboards, and a monitoring & evaluation framework

## 4.2 Out-of-Scope

Integration with government identity systems not yet available

Insurance platform integration, including national health insurance claims processing and adjudication (future phase)

Extension marketplace (future phase)

USSD gateway for feature phones (future phase)

Wearable device integration beyond commercially available APIs

Cross-border (East African Community) health data exchange (planned for a future regional-expansion phase; current architecture is designed to support it but exchange is not activated in this phase)

## 4.3 Boundaries

The system is designed for national-scale deployment within Uganda, with architecture supporting future East African expansion. It is an API-first, headless-capable platform that exposes all core functionality through documented APIs consumed by web, mobile, and third-party clients. The implementation phase concludes with a structured post-go-live stabilization (hypercare) period before full operational handover to a permanent Ministry of Health ICT and Digital Health Division team.

## 4.4 Scope Diagram

OUT OF SCOPE

IN SCOPE

Patient-facing services: account management, EHR access, appointment booking, telemedicine, AI health assistant, facility discovery and navigation, emergency assistance, online pharmacy, payments, health monitoring, medication reminders, pharmacovigilance reporting, reviews and notifications

Health facility services: registration and verification, staff and patient management, EMR, telemedicine, pharmacy and laboratory operations, order and delivery management, emergency services, location and mapping, financial management, reviews, pharmacovigilance, reporting, and notifications

Healthcare personnel services: professional profile management, availability and scheduling, patient search and access, clinical consultation management, telemedicine, prescription management, laboratory and diagnostic requests, referral management, emergency response, pharmacist and laboratory functions, care coordination, pharmacovigilance, health monitoring, reviews, reporting, and notifications

System administration: user, facility, and personnel lifecycle management; content and catalog governance; transaction oversight; security and audit administration; system configuration; monitoring; backup and recovery

Regulatory oversight: facility and personnel oversight; prescription and medicine oversight; pharmacovigilance management; public health surveillance; inspection management; complaint investigation; national health analytics

Audit capabilities: audit trail management; compliance auditing; financial auditing; security auditing

Developer ecosystem: REST and GraphQL APIs; webhooks; SDKs; plugin framework; healthcare interoperability standards (HL7, FHIR, ICD, SNOMED CT, LOINC)

GIS capabilities: facility geocoding; map tile services; routing and navigation; geospatial analytics; emergency location services

Security, privacy, and compliance services: end-to-end encryption, encryption key management, consent management, role-based access control, access auditing, and data subject rights handling under Uganda's Data Protection and Privacy Act

Capacity building and support: healthcare-worker digital literacy training, facility administrator onboarding, multi-channel help desk and support services, district-level adoption dashboards, and a monitoring & evaluation framework

Integration with government identity systems not yet available

Insurance platform integration, including national health insurance claims processing and adjudication (future phase)

Extension marketplace (future phase)

USSD gateway for feature phones (future phase)

■ In Scope (green)   ■ Out of Scope (red)

Figure 3: Scope Boundary — In-Scope vs Out-of-Scope

# 5. STAKEHOLDERS

## 5.1 Stakeholder Register

| ID | Name | Role | Organization | Power | Interest |
| --- | --- | --- | --- | --- | --- |
| SH-01 | Patients | End Users | General Public | Low | High |
| SH-02 | Healthcare Facilities | Service Providers | Hospitals, Clinics, Pharmacies, Laboratories | High | High |
| SH-03 | Healthcare Personnel | Clinical Staff | Doctors, Nurses, Pharmacists, Community Health Workers | High | High |
| SH-04 | System Administrators | Platform Operators | ICT Department | High | High |
| SH-05 | Ministry of Health | Regulator | Government | High | High |
| SH-06 | National Drug Authority | Regulator | Government | High | High |
| SH-07 | Auditors | Oversight | Internal/External Audit | Low | High |
| SH-08 | Researchers | Data Users | Academic/Research Institutions | Low | High |
| SH-09 | Developers | Integrators | Third-party Developers, System Integrators | Low | High |
| SH-10 | Development Partners / Donors | Funding & Technical Assistance Partners | WHO, USAID, Global Fund, World Bank | High | High |
| SH-11 | Civil Society & Patient Advocacy Groups | Community Representatives | NGOs, Patient Advocacy Networks | Low | High |
| SH-12 | Pharmaceutical Suppliers & Distributors | Supply Chain Partners | Licensed Wholesalers and Manufacturers | Low | Low |

## 5.2 Stakeholder Matrix

POWER →

INTEREST →

KEY PLAYERS

(Manage Closely)

KEEP SATISFIED

KEEP INFORMED

MONITOR

Patients

End Users

Healthcare Facilities

Service Providers

Healthcare Personnel

Clinical Staff

System Administrators

Platform Operators

Ministry of Health

Regulator

National Drug Authority

Regulator

Auditors

Oversight

Researchers

Data Users

Developers

Integrators

Development Partners / Donors

Funding & Technical Assistance Partners

Civil Society & Patient Advocacy Groups

Community Representatives

Pharmaceutical Suppliers & Distributors

Supply Chain Partners

■ Key Players  ■ Keep Satisfied  ■ Keep Informed  ■ Monitor

Figure 2: Stakeholder Power-Interest Matrix

# 6. SYSTEM CONTEXT

System context diagram (when provided).

## 6.2 Context Diagram

National Integrated Healthcare Ecosystem (NIHE)

Patients

Healthcare Facilities

Healthcare Personnel

System Administrators

Figure 7: NIHE System Context — External Interactions

# 7. PROJECT ORGANIZATION

## 7.1 Team Structure

| ID | Name | Role | Reports To |
| --- | --- | --- | --- |
| SPONSOR | Permanent Secretary | Project Sponsor | — |
| PM | Digital Health Division Lead | Project Manager | SPONSOR |
| ARCH | Chief Architect | Lead Architect | PM |
| BACKEND | Backend Lead | Backend Development Lead | ARCH |
| FRONTEND | Frontend Lead | Frontend Development Lead | ARCH |
| GIS | GIS Specialist | GIS Development Lead | ARCH |
| SEC | Security Lead | Cybersecurity & Information Security Lead | ARCH |
| DEVREL | Developer Relations | Developer Experience Lead | PM |
| QA | QA Lead | Quality Assurance Lead | PM |
| OPS | DevOps Lead | Operations and Infrastructure Lead | PM |
| DPO | Data Protection Officer | Privacy & Compliance Lead | PM |
| TRAIN | Training & Change Management Lead | Capacity Building Lead | PM |
| ME | Monitoring & Evaluation Lead | M&E Lead | PM |
| PROC | Procurement Lead | Procurement & Vendor Management Lead | PM |

## 7.2 Org Chart

Permanent Secretary

Project Sponsor

Digital Health Division Lead

Project Manager

Chief Architect

Lead Architect

Developer Relations

Developer Experience Lead

QA Lead

Quality Assurance Lead

DevOps Lead

Operations and Infrastructure Lead

Data Protection Officer

Privacy & Compliance Lead

Training & Change Management Lead

Capacity Building Lead

Monitoring & Evaluation Lead

M&E Lead

Procurement Lead

Procurement & Vendor Management Lead

Backend Lead

Backend Development Lead

Frontend Lead

Frontend Development Lead

GIS Specialist

GIS Development Lead

Security Lead

Cybersecurity & Information Security Lead

Figure 4: NIHE Project Organization Structure

# 8. CONSTRAINTS & ASSUMPTIONS

## 8.1 Constraints

Must operate under low-bandwidth conditions (≤ 100 Kbps) representative of rural Uganda

Must support intermittent connectivity with offline capabilities for critical functions

Must comply with Uganda's Data Protection and Privacy Act and healthcare regulatory requirements administered by the Ministry of Health and National Drug Authority

Must support Mobile Money as a primary payment method

Must support HL7/FHIR interoperability standards for integration with existing systems

Must be deployable on cloud, on-premises, or hybrid infrastructure

Must support 99.9% uptime for all critical services

Must support patient-facing content in English, Luganda, Runyankole, Luo, and other major Ugandan languages

Must comply with Uganda's Public Procurement and Disposal of Public Assets Authority (PPDA) regulations for all hardware, software, and vendor contracts

## 8.2 Assumptions

Patients, healthcare personnel, and facility staff have access to internet-connected smartphones, tablets, or computers, even if connectivity is intermittent or low-bandwidth

Healthcare facilities and personnel onboarding possess valid licensure and legal authority to deliver registered services

Cooperation from healthcare facilities and regulatory bodies (MoH, NDA) for credential verification is available

Third-party Mobile Money, SMS, email, and mapping service providers maintain acceptable service levels

Future integration with government identity, insurance, and national health systems will be possible

The platform will achieve sufficient adoption to realize national-scale benefits

National electricity supply and data-center infrastructure will provide sufficient reliability for primary and backup hosting sites

The Ministry of Health will provide sustained budgetary support beyond the initial implementation period for ongoing operations and maintenance

# 9. RISKS

## 9.1 Risk Register

| ID | Risk | Likelihood | Impact | Mitigation |
| --- | --- | --- | --- | --- |
| RSK-01 | Limited internet connectivity in rural areas may reduce platform adoption and usability | 4 | 5 | Implement offline-first architecture, data compression, USSD fallback, and progressive web app capabilities |
| RSK-02 | Resistance to digital adoption from healthcare workers and facilities | 3 | 4 | Comprehensive training programs, stakeholder engagement, pilot testing, user-centred design |
| RSK-03 | Data privacy and security breaches compromising patient information | 2 | 5 | End-to-end encryption, role-based access control, regular security audits, compliance with Uganda Data Protection Act |
| RSK-04 | Interoperability challenges with existing healthcare systems | 3 | 4 | Adopt HL7/FHIR standards, provide integration SDKs, API-first architecture, partner engagement |
| RSK-05 | Project funding constraints may impact scope or timeline | 3 | 4 | Phased delivery approach, prioritise core functionality, secure government and donor funding |
| RSK-06 | Regulatory changes affecting healthcare data handling or telemedicine | 2 | 4 | Engage regulators early, build flexible compliance framework, regular legal review |
| RSK-07 | Insufficient GIS data quality for routing and facility location | 3 | 3 | Ground-truthing validation, community mapping partnerships, leverage OpenStreetMap |
| RSK-08 | Cybersecurity threats, including ransomware and data breaches, targeting national health infrastructure | 3 | 5 | Defense-in-depth security architecture, 24/7 security operations monitoring, regular penetration testing, documented incident response plan, cyber insurance |
| RSK-09 | Attrition of key technical personnel (architects, GIS specialists, security leads) during the project lifecycle | 3 | 4 | Competitive retention packages, thorough knowledge documentation, cross-training, succession planning, partnerships with local universities for talent pipeline |
| RSK-10 | Over-dependence on third-party vendors (cloud, payment, mapping) creating lock-in or service-continuity risk | 2 | 3 | Multi-vendor strategy where feasible, contractual SLAs, data portability requirements, defined exit clauses in vendor contracts |
| RSK-11 | Poor data quality and migration errors when importing legacy paper-based or fragmented digital records | 4 | 3 | Pre-migration data quality audits, phased data validation, dedicated data migration team, tested rollback procedures |

## 9.2 Problem Tree Analysis

#E65100

#B71C1C

#B71C1C

#B71C1C

#B71C1C

#B71C1C

#0D47A1

#0D47A1

#0D47A1

#0D47A1

#1B5E20

#1B5E20

#1B5E20

Figure 1: Problem Tree — Uganda Healthcare Ecosystem Challenges

## 9.3 Risk Matrix

LIKELIHOOD ↑

IMPACT →

1

1

2

2

3

3

4

4

5

5

RSK-01

RSK-02

RSK-03

RSK-04

RSK-05

RSK-06

RSK-07

RSK-08

RSK-09

RSK-10

RSK-11

■ Critical  ■ High  ■ Medium  ■ Low

Figure 6: NIHE Risk Matrix

# 10. MILESTONES

## 10.1 Milestone Schedule

| ID | Milestone | Date | Deliverable |
| --- | --- | --- | --- |
| M1 | Project Kick-off | 2026-07-01 | Project charter approved, team assembled |
| M2 | Requirements Finalization | 2026-09-30 | Complete SRS approved by all stakeholders |
| M3 | System Architecture Design | 2026-11-30 | Architecture diagrams, technology stack finalized |
| M4 | GIS Platform Prototype | 2027-02-28 | Working map tile server, geocoding, and routing prototype |
| M5 | Core EHR Module Complete | 2027-05-31 | Patient records, facility management, appointment system |
| M6 | Security & Compliance Certification | 2027-07-15 | Independent security audit passed; Data Protection Impact Assessment approved by regulators |
| M7 | Pilot Deployment | 2027-08-31 | Live system in 5 pilot districts |
| M8 | National Rollout Phase 1 | 2028-01-31 | System live in 50% of districts |
| M9 | Full National Deployment | 2028-06-30 | 100% district coverage, all core modules live |
| M10 | Post-Go-Live Stabilization & Handover | 2028-09-30 | Hypercare support period complete; operations handed to permanent Ministry of Health ICT team; lessons-learned report published |

## 10.2 Timeline

Initiation

Design

Build

Deploy

2026-07-01

Project Kick-off

2026-09-30

Requirements Finalization

2026-11-30

System Architecture Design

2027-02-28

GIS Platform Prototype

2027-05-31

Core EHR Module Complete

2027-07-15

Security & Compliance Certification

2027-08-31

Pilot Deployment

2028-01-31

National Rollout Phase 1

2028-06-30

Full National Deployment

2028-09-30

Post-Go-Live Stabilization & Handover

● Milestone   │ Phase band   — Red = critical

Figure 5: NIHE Implementation Timeline

# 11. BUDGET

| Category | Amount (USD) |
| --- | --- |
| Personnel | 450,000 |
| Hardware | 400,000 |
| Software | 200,000 |
| Training | 150,000 |
| Contingency | 50,000 |
| TOTAL | 1,250,000 |

# 12. SUCCESS CRITERIA

Patient record retrieval time ≤ 2 seconds

System uptime ≥ 99.9%

Emergency dispatch automation ≤ 2 minutes

National facility mapping coverage 100% of districts

Multi-facility interoperability via HL7/FHIR

Medicine inventory accuracy ≥ 98%

Regulatory compliance rate 100%

100% of registered healthcare facilities using the platform

Video consultation quality score ≥ 4/5

ADR report acknowledgment time ≤ 4 hours

Zero critical (Severity 1) security incidents during the first 12 months post-launch

≥ 90% of onboarded healthcare personnel digitally certified on platform use

Help desk first-response time ≤ 30 minutes during business hours

# 13. APPROVALS

| Role | Name | Signature | Date |
| --- | --- | --- | --- |
| Project Sponsor | Ministry of Health Representative |  | 2026-07-15 |
| Project Manager | Digital Health Division Lead |  | 2026-07-01 |
| Technical Lead / Architect | Chief Architect |  | 2026-07-10 |
| Data Protection Officer | Ministry of Health Data Protection Officer |  | 2026-07-12 |
| National Drug Authority Representative | NDA Liaison Officer |  | 2026-07-14 |